## Action Plan 2021-2022
The social value strategy action plan for 2021-2022 is shown.
SOCIAL VALUE STRATEGY - ACTION PLAN 21/22
Green - Started | Q1 - 1 April
Amber - not started | Q2 - 1 July
Red - delay | Q3 - 1 Oct
Q4 - 1 Jan
THEMES | OBJECTIVE | ACTION | RESPONSIBLE | STATUS | START | END | NOTES
COMMISSIONING | Build a shared social value understanding | Trainings roll out for commissioners across all areas | Social Value Lead | Blank cell | Q1 | Blank cell | Blank cell
COMMISSIONING | Build a shared social value understanding | Ammend Procurment strategy template and award report to include Local Economy and Social Value outcomes | Social Value Lead & Governance team | Blank cell | 2021-01-01 | Blank cell | Blank cell
COMMISSIONING | Build a shared social value understanding | Q&A sessions bi-monthy for commissioners | Social Value Lead | Blank cell | Q1 | Blank cell | Blank cell
COMMISSIONING | Build a shared social value understanding | Create and maintain a record of stakeholders' feedback | Social Value Lead | Blank cell | 2021-01-01 | Ongoing | Blank cell
COMMISSIONING | Build a shared social value understanding | Council wide communication campaing, internal newslatters and intranet | Social Value Lead & Comms | Blank cell | Q1 | Blank cell | Blank cell
COMMISSIONING | Build a shared social value understanding | Re- engage with Internal Social Value Delivery Group (SVDG) | Social Value Lead | Blank cell | Q2 | Blank cell | Blank cell
MARKET ENGAGEMENT AND PARTNERSHIP | Create Business Network and collect feedback | Crate a record of case studies and capturing innovation | Social Value Lead & Head of Porcurement | Blank cell | Q1 | 2022-03-31 | Blank cell
MARKET ENGAGEMENT AND PARTNERSHIP | Create Business Network and collect feedback | Organise market engagement with suppliers across all service areas - quartery | Social Value Lead, Business and Enterprise Team & Head of Porcurement | Blank cell | 2021-01-01 | Ongoing | Blank cell
MARKET ENGAGEMENT AND PARTNERSHIP | Create Business Network and collect feedback | Create a regular forum for suppliers to network and share best practice and collaborate on Social Value | Social Value Lead & Business and Enterprise | Blank cell | Q2 | Ongoing | Blank cell
MARKET ENGAGEMENT AND PARTNERSHIP | Create Business Network and collect feedback | Promote B2B relationships for larger suppliers and long term frameworks | Head of Porcurement / Social Value Lead | Blank cell | Q2 | Blank cell | Blank cell
MARKET ENGAGEMENT AND PARTNERSHIP | Create Business Network and collect feedback | Create annual suppliers satisfaction survey | Head of Porcurement / Commissioners & Social Value Lead | Blank cell | Q4 | Blank cell | Blank cell
CONTRACT MANAGEMENT | Record information | Create a record of lesson learnt to highlight areas of improvements | Head of Porcurement & Social Value | Blank cell | 2021-01-01 | Ongoing | Blank cell
CONTRACT MANAGEMENT | Record information | Benchmark Economic Development activity with other Councils to establish best practice | Social Value Lead | Blank cell | Q3 | Blank cell | Blank cell
INTERNAL MANAGEMENT | SV Cabinet reporting KPI | Departmental Cabinet Member briefings - amend templates to include a section on social value | Social Value Lead | Blank cell | Q2 | Blank cell | Blank cell
INTERNAL MANAGEMENT | SV Cabinet reporting KPI | Establish Baseline of current contracts which have Social Value outcomes | Social Value Lead | Blank cell | 2021-01-01 | Ongoing | Blank cell
INTERNAL MANAGEMENT | SV Cabinet reporting KPI | Create a dashborad to report to SLT & Cabinet | Social Value Lead, Head of Economic Development & Head of Porcurement | Blank cell |  | Blank cell | Blank cell
POLICY & SCOPE | Expand the Social Value Strategy to apply to Grant Allocations and synergies with S106 and Planning. | Attend the national task force for SV in Planning | Social Value Lead & Head of Porcurement S106 Officer | Blank cell | 2021-01-12 | Ongoing | Blank cell
POLICY & SCOPE | Expand the Social Value Strategy to apply to Grant Allocations and synergies with S106 and Planning. | Form an internal working group with relevant stakeholders to explore SV in Planning and, to focus on Economic Development outcomes | Social Value Lead & Head of Porcurement S106 Officer | Blank cell | Q2 | Blank cell | Blank cell
POLICY & SCOPE | Expand the Social Value Strategy to apply to Grant Allocations and synergies with S106 and Planning. | Form an internal working group with relevant stakeholders to explore SV in Grants Allocations | Social Value Lead & Head of Porcurement | Blank cell | Q3 | Blank cell | Blank cell
POLICY & SCOPE | Expand the Social Value Strategy to apply to Grant Allocations and synergies with S106 and Planning. | Reviews of relevant strategies following review of Grants Allocation/ Planning | Social Value Lead, Head of Economic Development & Head of Porcurement | Blank cell | Q3 | Blank cell | Blank cell
MEASUREMENT OF TOMs | Consultation with stakeholders | Engage with other public sectors services (e.g. NHS) to support alignment with Local TOMs linked to Economic Development outcomes. Also work to support wider take up of social value activities. | Social Value Lead & Head of Economic Development | Blank cell | Q3 | Blank cell | Blank cell
MEASUREMENT OF TOMs | Consultation with stakeholders | Engage with local communities / service users to feed to continue developmemt of TOMs | Social Value Lead | Blank cell | Q2 | Blank cell | Blank cell
MEASUREMENT OF TOMs | Consultation with stakeholders | Engage with Local Businesses through existing H&F networks to raise awareness of social value approach and receive feedback | Social Value Lead | Blank cell | Q1 | Blank cell | Blank cell
MEASUREMENT OF TOMs | Consultation with stakeholders | Capture residents feedback on H&F TOMs and include in the annual report | Social Value Lead & Commissioners | Blank cell | Q2 | Q3 | Blank cell
PROCUREMENT | Residents involvment - involve more residents give opportunity to evaluate bidders commitments at tender stage | Liaise with Co-production team - to identify ways to increase residents involvment in procurement evaluation | Head of Porcurement & Social Value Lead | Blank cell | Q2 | Blank cell | Blank cell
PROCUREMENT | Residents involvment - involve more residents give opportunity to evaluate bidders commitments at tender stage | Explore a campaign to give residents and service users the opportunity to be part of the evaluation group for sv submissions | Head of Procurement / Commissioners & Social Value Lead | Blank cell | Q2 | Blank cell | Blank cell
REPORTING | Showcase and public communication | Share geospatial mapping and digital communication with residents and stakeholder to show impact | Social Value Lead & Social Value Portal (SVP) | Blank cell | Q2 | Ongoing | Blank cell
REPORTING | Showcase and public communication | Create Communication plan for internal and external stakeholders | Social Value Lead | Blank cell | 2021-01-01 | Ongoing | Blank cell
REPORTING | Showcase and public communication | Publish regular case studies | Social Value Lead & Commissioners | Blank cell | Q1 | Ongoing | Blank cell
GOVERNANCE & ACCOUNTABILITY | Cross department Scrutiny | Report annually to Cabinet | Social Value Lead & Head of Economic Development | Blank cell | Q2 | Blank cell | Blank cell
GOVERNANCE & ACCOUNTABILITY | Cross department Scrutiny | Monitor departmental annual target 10% social value across contracts | Head of Procurement Social Value Lead | Blank cell | Q1 | Ongoing | Blank cell
End of the sheet